## Sprint1
WEEK 1 (28thFeb - 6th March) - SPRINT 1
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Understand the requirements, explore other hotel websites & work on project sheet | Decide on scrum meetings & Setting up Project | None
Sharan Santosh Rachamalla | Figure out the components in the project | Setting up project tech stack | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Figure out the technologies | Setting up project tech stack & read about tech stack | None
Prerna Dattatray Garsole | Figure out the pages design to be included | Setting up project tech stack & read about tech stack | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We aimed at generating simple ideas to meet the requirements of the project
2. Communication | Everybody provided their inputs about the various possible scenarios according to problem statement and provided their opinions on what might be a better approach

## Sprint2
WEEK 2 (7th March - 13th March) - SPRINT 2
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Configure the project i.e ReactJs & NodeJS | Need to database design | None
Sharan Santosh Rachamalla | Configure the project i.e ReactJs & NodeJS | Need to database design | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Configure the project i.e ReactJs & NodeJS | Create Architecture | None
Prerna Dattatray Garsole | Configure the project i.e MongoDB | Create Class Diagram | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We aimed at choosing simple frameworks and technologies
2. Communication | Clearly communicated the ideas about how the technologies will be working together towards the completion of project
3. Feedback | Everybody was involved in planning which tech stack we had to use

## Sprint3
WEEK 3 (14th March - 20th March) - SPRINT 3
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Completed database schema for hotels & bookings | Create Search API | None
Sharan Santosh Rachamalla | Completed database schema for users & rooms | Figure out holiday, weekend & seasonal pricing logic | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Completed architecture diagram | Create Signup & login API | None
Prerna Dattatray Garsole | Completed class diagram | Design wireframes for SignUp & Login | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We came up with simple UI wireframes which are easy to build but serves the purpose
2. Communication | We communicated and decided on which modules everybody has to work
3. Feedback | According to the feedback from everyone, we decided to do a rotation of scrum master so that everybody gets the chance to conduct scrum

## Sprint4
WEEK 4 (21st March - 27th March) - SPRINT 4
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Completed Search API | Create Search UI & Work on Admin API | None
Sharan Santosh Rachamalla | Completed logic for holiday, weekend & seasonal pricing | Create Hotel UI | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Completed sign up & login apis | Create logout & userprofile API | None
Prerna Dattatray Garsole | Completed wireframes design for signup & login | Create wireframes for Hotel Page & UI pages for Login & Sign Up | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We created simple website designs
2. Communication | Everybody participated in communicating their ideas on how the project needs to shape and we moved in that direction
3. Feedback | We provided feedback on the designs and implemented the ones which had a better reasoning

## Sprint5
WEEK 5 (28th March - 4th April) - SPRINT 5
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Completed Search UI & Admin CRUD APIs | Create Admin UI | None
Sharan Santosh Rachamalla | Completed Hotel UI | Create Room UI | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Completed logout & userprofile APIs | Create User Profile UI | None
Prerna Dattatray Garsole | Completed Hotel Wireframe & UI Pages for Singup & Login | Create User Profile Wireframe | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We decided on a simple website design
2. Communication | Everybody communicated on how the design patterns can be added and why the design patterns worked the best for our project
3. Feedback | Everybody provided feedback on the ui screens and few labels and css were changed

## Sprint6
WEEK 6 (4th April - 10th April) - SPRINT 6
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Completed Admin UI | Create CRUD Bookings API | None
Sharan Santosh Rachamalla | Completed Room UI | Create Bookings UI | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Completed User Profile UI | Create Mockdata for tables & Start Testing | None
Prerna Dattatray Garsole | Completed User Profile Wireframe | Create Bookings Wireframe | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We decided on a simple database design with proper relations
2. Communication | Everybody communicated their ideas on how we can handle errors and provide proper validation to all the components
3. Feedback | All the feedback regarding error handling was taken positively and implemented

## Sprint7
WEEK 7 (11th April - 17th April) - SPRINT 7
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Completed CRUD Bookings API | Start fixing the bugs | None
Sharan Santosh Rachamalla | Completed Bookings UI | Start fixing the bugs | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Created Mockdata & did Testing | Get Info about AWS Deployment | None
Prerna Dattatray Garsole | Completed Bookings Wireframe | Testing Parallely While others fixing bugs | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We decided on simple angular components for simplicity
2. Communication | Everybody communicated about the changes needed to few UI designs
3. Feedback | All the feedback regarding UI changes was taken positively and wireframes were implemented with new designs

## Sprint8
WEEK 8 (18th April - 24th April) - SPRINT 8
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Fixed Bugs | Check the gaps & bugs | None
Sharan Santosh Rachamalla | Fixed Bugs | Check the gaps & bugs | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Explored AWS Deployment with load balancer & auto scaling | QA Deployment | None
Prerna Dattatray Garsole | Testing | Continue Testing | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Simplicity | We decided on simple UI
2. Communication | Everybody communicated about the changes needed to few UI designs
3. Feedback | All the feedback regarding UI changes was taken positively and wireframes were implemented with new designs

## Sprint9
WEEK 9 (25th April - 1st May) - SPRINT 9
WEEKLY SCRUM REPORT
TEAM MEMBER | TASKS WORKED ON / COMPLETED | TASKS GOING TO WORK ON | BLOCKERS
Akhil Apparaju | Fixed Bugs |  | None
Sharan Santosh Rachamalla | Fixed Bugs |  | None
Tirupati Venkata Sri Sai Rama Raju Penmatsa | Deployment |  | None
Prerna Dattatray Garsole | Post deployment testing |  | None
SCRUM MASTER: Akhil Apparaju
XP CORE VALUES REPORT
CORE VALUES | HOW WE ADHERED TO CORE VALUES
1. Respect | Throughout the project development process we have respected each other's thought process and design thinking
2. Feedback | After all the feedback we received we decided to deploy both frontend and backend on different servers